COMBINED EXECUTION PLAN

Capability-at-a-Time Cross-Repository Implementation

6 Capabilities (32 build steps) → then 18 Risk Mitigations

All Three Repos Per Capability — Tested End-to-End Before Moving On

Open Source Stack: Hyperledger Fabric • OpenTimestamps • W3C DIDs • Synthea • ISCO-08

Date: 15 March 2026  |  Classification: Strategic

# 1. Why Capability-at-a-Time Wins

Three implementation strategies were evaluated. The capability-at-a-time approach (vertical slices across all repos per capability) is the only viable strategy for this workspace.

| Criterion | A. Repo-at-a-Time | B. All Parallel | C. Capability-at-a-Time | Verdict |
| --- | --- | --- | --- | --- |
| Testability | Cannot test until last repo done. GHARRA federation sits untested for weeks. | Nothing testable until all repos converge simultaneously. Integration failures discovered last. | Each capability tested end-to-end across all 3 repos before starting next. Failures caught early. | C wins |
| Calendar Time | Longest. Serial repo execution. ~40-50 days. | Shortest on paper (~15 days) but rework from integration failures adds ~10+ days. | Moderate. ~25-35 days. Each capability sprint is 2-8 days across all repos. | C is realistic |
| Dependency Chain | Broken. Cap 1 needs GHARRA + Integration simultaneously. Repo-sequential can't satisfy. | Ignored. Teams work on unrelated capabilities. Cross-cap dependencies (Cap 2 needs Cap 1) unsatisfied. | Respected. Build sequence Cap 4→1→5→2→6→3 ensures each capability's prerequisites are proven. | C wins |
| PR Review Quality | Massive PRs per repo (all caps in one batch). Hard to review, hard to bisect. | Many concurrent PRs across repos. Merge conflicts. Review overload. | Small, focused PRs: 1 per repo per capability. Reviewer understands scope. Easy to revert. | C wins |
| Risk Mitigation Readiness | Mitigations can't start until all repos finish all capabilities. Long delay. | Same issue: mitigations depend on working capabilities, not just code. | Each proven capability unlocks its mitigations immediately. Mitigation work can overlap with later capabilities. | C wins |
| Open Source Integration | Blockchain (Hyperledger) integration deferred until GHARRA repo turn. Long feedback loop. | Hyperledger, Synthea, DIDs integrated in parallel. Hard to debug interactions. | Each OSS component integrated when its capability is built: Synthea in Cap 4, DIDs in Cap 1, Hyperledger in Cap 5. Tested immediately. | C wins |

Decision: Capability-at-a-time (Option C) is the only approach that respects cross-repo dependencies, enables end-to-end testing per capability, and unblocks risk mitigations progressively.

# 2. Open Source Technology Stack

Every external technology in this plan is open source with permissive licensing. No vendor lock-in. No proprietary dependencies.

| Technology | Licence | Steward | Used In | Capability | Why This Choice |
| --- | --- | --- | --- | --- | --- |
| Hyperledger Fabric | Apache 2.0 | Linux Foundation | Mitigation 5.1 | Audit Trail | Already used in FDA DSCSA pilot and Pfizer/McKesson drug traceability. Permissioned (healthcare-appropriate). No public data exposure. Enterprise-grade. |
| OpenTimestamps | LGPL 3.0 | Community | Mitigations 2.2, 4.3 | Break-Glass + Benchmarks | Bitcoin-anchored timestamping. Free. No API keys. Decentralised proof-of-time. Used by Internet Archive. |
| W3C DIDs (did:web, did:ebsi) | W3C Open Standard | W3C + EU EBSI | Mitigations 1.2, 5.2 | Identity + IDs | W3C Recommendation (2022). did:web is zero-cost (HTTP). did:ebsi is EU-funded (EBSI v2). No per-identity fees. |
| Synthea Patient Generator | Apache 2.0 | MITRE / HL7 | Mitigation 4.1 | Scale Simulation | HL7-endorsed synthetic patient generator. Clinically validated. Used by ONC, CMS, and NHS Digital for testing. 100+ condition modules. |
| ISCO-08 Occupation Codes | Public Domain (ILO) | International Labour Organization | Mitigation 6.3 | Persona Scale | UN standard classification. ~430 health occupation codes. Used by all national workforce registries. No licensing fees. |
| GLEIF LEI Lookup API | Free API (CC0 data) | Global LEI Foundation | Mitigation 5.2 | Organisation IDs | ISO 17442 Legal Entity Identifiers. Free API for validation. Already mandatory in financial services. Machine-readable. |
| Python opentimestamps | LGPL 3.0 | Community | Mitigations 2.2, 4.3, 5.1 | Timestamp Anchoring | Python library for OpenTimestamps. pip install opentimestamps. Create and verify proofs. No dependencies on commercial timestamp services. |
| did-resolver (Python) | Apache 2.0 | DIF / Community | Mitigation 1.2 | DID Resolution | Decentralized Identity Foundation reference implementation. Resolves did:web, did:key, did:ebsi. Pluggable method drivers. |

Zero proprietary dependencies. Every component can be self-hosted, forked, and audited. Total licensing cost: £0.

# 3. Combined Execution Plan — Capability Sprints

Each capability sprint touches all three repos, ends with a tested integration gate, and unlocks specific risk mitigations.

| Sprint | Capability | Days | Integration Gate | Unlocked Mitigations | Open Source Introduced |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Capability 4: Scale Simulation | Days 1-3 | pytest tests/test_scale_simulation.py | 4.1 Synthea populations (Integration); 4.2 Cloud deployment profiles (Integration); 4.3 Benchmark tamper-proofing (GHARRA) | None in this sprint |
| Sprint 2 | Capability 1: Cross-Border Agent Routing | Days 4-8 | pytest tests/test_agent_resolution.py + tests/test_agent_routing.py | 1.1 TIA Engine (GHARRA); 1.2 DID Identity (GHARRA); 1.3 Enforcement Proxy (GHARRA) | W3C DIDs prepared for mitigation 1.2 (did-resolver library) |
| Sprint 3 | Capability 5: Tamper-Evident Audit Trail | Days 9-13 | pytest tests/test_observability.py | 5.1 Distributed Ledger / Hyperledger Fabric (GHARRA); 5.2 Identifier Standards (GHARRA); 5.3 GDPR Erasure Pattern (GHARRA) | Hyperledger Fabric (Apache 2.0) + OpenTimestamps (LGPL) prepared for mitigations 5.1 + 2.2 |
| Sprint 4 | Capability 2: Policy-Aware Intelligent Routing | Days 14-19 | pytest tests/test_policy_enforcement.py | 2.1 Policy Governance Board (GHARRA); 2.2 Break-Glass (GHARRA); 2.3 Multi-layer PHI Detection (GHARRA) | None new in this sprint |
| Sprint 5 | Capability 6: Persona-Adaptive Clinical Workflows | Days 20-24 | pytest tests/test_signalbox_workflow.py | 6.1 Framework Validation Programme (Nexus); 6.2 Equity Monitoring (Integration); 6.3 ISCO-08 Composable Personas (Nexus) | ISCO-08 (ILO public domain) prepared for mitigation 6.3 |
| Sprint 6 | Capability 3: Self-Healing Clinical Agent Mesh | Days 25-32 | pytest tests/test_agent_routing.py + tests/test_signalbox_workflow.py | 3.1 IEC 62304 Classification (Nexus); 3.2 Durable Event Sourcing (Nexus); 3.3 Agent Equivalence Registry (GHARRA) | None new in this sprint |

Total: 6 sprints, ~32 working days. Each sprint ends with a passing integration test gate. No capability proceeds without the previous gate passing.

# Sprint 1: Capability 4: Scale Simulation

Timeline: Days 1-3

WHY NOW: Fix the test foundation. Every subsequent capability depends on being able to run integration tests against live services.

## Work per Repository

| GHARRA (global-agent-registry/) | Nexus (Nexus-A2A-protocol/) | Integration (integration/) |
| --- | --- | --- |
| Add healthcheck endpoint validation (already exists, ensure reliability) Verify agent seed returns 200 for all 6 default agents | Add healthcheck to on_demand_gateway (if missing) Verify all test agents respond to /health | Fix conftest.py: add wait_for_services() with 60s retry Fix docker-compose.yml: add healthcheck + depends_on with condition: service_healthy Add warmup phase to scale_simulation.py Add report metadata (deployment_context, infrastructure, caveats, report_hash) Run smoke + small profiles successfully Save reports to integration/reports/ |

## Integration Gate (Must Pass Before Next Sprint)

pytest tests/test_scale_simulation.py — smoke + small pass with 80%+ success rate, reports saved with metadata

## Risk Mitigations Unlocked

- 4.1 Synthea populations (Integration)

- 4.2 Cloud deployment profiles (Integration)

- 4.3 Benchmark tamper-proofing (GHARRA)

# Sprint 2: Capability 1: Cross-Border Agent Routing

Timeline: Days 4-8

WHY NOW: Keystone capability. Federation is the platform differentiator. Caps 2, 3, 5 all depend on multi-registry routing working.

## Work per Repository

| GHARRA (global-agent-registry/) | Nexus (Nexus-A2A-protocol/) | Integration (integration/) |
| --- | --- | --- |
| Implement PeerRegistryManager in federation.py Add GHARRA_KNOWN_PEERS and GHARRA_PARENT_REGISTRY_URL config Sovereign auto-registration with root on startup Wire peer discovery in api/main.py startup event Ensure /v1/registries creates CRI cache entry for new sovereign | Verify route_admission.py handles federated record flag correctly Verify X-Gharra-Record header propagation across agent invocations Ensure correlation_id flows across jurisdictional boundaries | Add gharra-sovereign-gb (port 8401) and gharra-sovereign-us (port 8402) to docker-compose.yml Set root GHARRA to GHARRA_TIER=root with KNOWN_PEERS pointing to sovereigns Extend seed.py to register jurisdiction-specific agents per sovereign Add conftest fixtures: gharra_gb_url, gharra_us_url Write federated discovery tests (cross-jurisdiction, circuit breaker, CRI cache) Write cross-border workflow runner and invoke tests |

## Integration Gate (Must Pass Before Next Sprint)

pytest tests/test_agent_resolution.py + tests/test_agent_routing.py — federated discovery returns agents from GB+US, cross-border invoke succeeds

## Risk Mitigations Unlocked

- 1.1 TIA Engine (GHARRA)

- 1.2 DID Identity (GHARRA)

- 1.3 Enforcement Proxy (GHARRA)

## Open Source Components

W3C DIDs prepared for mitigation 1.2 (did-resolver library)

# Sprint 3: Capability 5: Tamper-Evident Audit Trail

Timeline: Days 9-13

WHY NOW: Routing decisions must be auditable before policy enforcement begins. Underpins governance for all subsequent capabilities.

## Work per Repository

| GHARRA (global-agent-registry/) | Nexus (Nexus-A2A-protocol/) | Integration (integration/) |
| --- | --- | --- |
| Expand OPERATION_TYPES: add routing.resolved, routing.denied, policy.evaluated, discovery.completed, federation.query Add ledger.append() calls in routing.py, discover.py, policy.py for new event types Wire PolicyEngine audit callback to ledger via api/main.py Implement BackgroundVerifier: verify_chain() every 5 mins, health check degraded on failure Add real-time ledger event streaming via SSE (events.py with ledger.* filter) Include ledger verification status in /health endpoint | Add audit event emission from gateway: invocation events, handoff events (prep for Cap 3) Ensure all gateway operations include correlation_id for audit correlation | Complete FHIR AuditEvent mapping: agent_role_code, entity_role, source_observer_type, network_address Add to_fhir_bundle() for batch audit export Write tests: ledger records routing decisions, policy denials, background verification, SSE streaming Verify FHIR R4 AuditEvent compliance for all new operation types |

## Integration Gate (Must Pass Before Next Sprint)

pytest tests/test_observability.py — routing + policy decisions in ledger, background verifier running, SSE streaming works, FHIR mapping complete

## Risk Mitigations Unlocked

- 5.1 Distributed Ledger / Hyperledger Fabric (GHARRA)

- 5.2 Identifier Standards (GHARRA)

- 5.3 GDPR Erasure Pattern (GHARRA)

## Open Source Components

Hyperledger Fabric (Apache 2.0) + OpenTimestamps (LGPL) prepared for mitigations 5.1 + 2.2

# Sprint 4: Capability 2: Policy-Aware Intelligent Routing

Timeline: Days 14-19

WHY NOW: Enforcement layer. PHI detection and consent validation build on existing policy engine. Needs routing + audit working first.

## Work per Repository

| GHARRA (global-agent-registry/) | Nexus (Nexus-A2A-protocol/) | Integration (integration/) |
| --- | --- | --- |
| Extend bullettrain.py classify_request() with value-level PHI pattern inspection (SSN, NHS, email, DOB, phone) Add classify_with_evidence() returning PHI evidence array Implement POST /v1/route/enforce endpoint (enforcement bridge) Replace _check_phi_block() in gateway.py with new PHI classifier Add consent proof JWT validation in ConsentGateRule (parse, verify signature, check expiry) Implement policy hot-reload: _RULE_REGISTRY, load_rules_from_config(), reload_rules() Add PUT /v1/admin/policy/rules endpoint for hot-reload API | In POST /rpc/{agent_alias}: if NEXUS_GHARRA_ENFORCE_POLICY=true, call GHARRA /v1/route/enforce before dispatch If enforcement denied: return 403 with policy violations Add NEXUS_GHARRA_BASE_URL env var for enforcement calls Add X-Policy-Obligations response header for permitted-with-conditions | Write PHI detection tests: SSN in free text, NHS number, email, clean clinical data Write enforcement bridge tests: PHI payload to non-PHI agent blocked, clean payload permitted Write consent JWT tests: valid JWT permits, expired JWT denied Write policy hot-reload test: reload rules via API, verify new rule in effect Set NEXUS_GHARRA_ENFORCE_POLICY=true in docker-compose for test environment |

## Integration Gate (Must Pass Before Next Sprint)

pytest tests/test_policy_enforcement.py — PHI detection catches SSN/NHS/email, enforcement bridge blocks non-compliant routing, consent JWT validated, hot-reload works

## Risk Mitigations Unlocked

- 2.1 Policy Governance Board (GHARRA)

- 2.2 Break-Glass (GHARRA)

- 2.3 Multi-layer PHI Detection (GHARRA)

# Sprint 5: Capability 6: Persona-Adaptive Clinical Workflows

Timeline: Days 20-24

WHY NOW: Clinical differentiation. Persona-influenced routing needs policy engine. Framework prompt integration is independent but completes the persona system.

## Work per Repository

| GHARRA (global-agent-registry/) | Nexus (Nexus-A2A-protocol/) | Integration (integration/) |
| --- | --- | --- |
| Accept persona_context in RoutingRequest: {persona_id, rbac_level, purpose_of_use, data_sensitivity} Filter candidates by persona sensitivity and purpose_of_use compatibility Include persona_context in routing audit log (ledger entry) | Framework-to-prompt integration: load framework SYSTEM_PROMPT_TEMPLATE in avatar_engine.py start_session() Add SYSTEM_PROMPT_TEMPLATE constants to abcde.py, socrates.py, calgary_cambridge.py Inject persona communication_style + specialty into LLM system prompt Extract persona context from JWT claims in gateway, pass to GHARRA routing Implement persona switching: persona_broker.switch_persona() + persona/switch RPC handler Add FRAMEWORK_COUNTRY_MATRIX and country fallback logic in framework_selector.py | Write tests: framework prompt injection, persona style in prompt, persona influences routing Write tests: persona switch during workflow, country framework fallback Verify persona-stratified metrics can be collected in simulation |

## Integration Gate (Must Pass Before Next Sprint)

pytest tests/test_signalbox_workflow.py — framework instructions in LLM prompt, persona drives routing, switching works, country fallback safe

## Risk Mitigations Unlocked

- 6.1 Framework Validation Programme (Nexus)

- 6.2 Equity Monitoring (Integration)

- 6.3 ISCO-08 Composable Personas (Nexus)

## Open Source Components

ISCO-08 (ILO public domain) prepared for mitigation 6.3

# Sprint 6: Capability 3: Self-Healing Clinical Agent Mesh

Timeline: Days 25-32

WHY NOW: Hardest capability. Needs routing + policy + audit all working. Failover depends on alternatives from routing. Handoff rules need gateway integration.

## Work per Repository

| GHARRA (global-agent-registry/) | Nexus (Nexus-A2A-protocol/) | Integration (integration/) |
| --- | --- | --- |
| Ensure RoutingResponse.alternatives[] always populated when multiple endpoints exist Sort alternatives by priority + weight Include endpoint health hints from last-known status | Integrate handoff rules into gateway: apply_nhs_guardrails() in POST /rpc/{agent_alias} after response Add build_step_from_rpc() and build_context_from_params() helpers for RPC-to-step bridging Implement tasks/resubscribe RPC handler with replay_from_cursor() Enable JSONL event persistence by default (NEXUS_TASK_EVENT_STORE_PATH auto-generated) Add cursor_remaining_ms() helper for client-side monitoring Implement automatic failover: on 5xx, select alternative from GHARRA, retry (max 2 attempts) Add X-Failover-From / X-Failover-To headers Implement BackgroundHealthProber: probe /health every 30s, restart after 3 consecutive failures Add SessionStore for avatar_engine: save_session() / load_session() with JSONL persistence | Write tests: handoff guardrail blocks unsafe discharge, permits safe discharge Write tests: stream resubscribe with valid cursor, expired cursor returns replay instruction Write tests: agent failover on 5xx, health probe detects failure Write tests: clinical handoff in gateway production path, deterioration escalation triggers |

## Integration Gate (Must Pass Before Next Sprint)

pytest tests/test_agent_routing.py + tests/test_signalbox_workflow.py — handoff rules live in gateway, stream resume works, automatic failover succeeds, health probing runs

## Risk Mitigations Unlocked

- 3.1 IEC 62304 Classification (Nexus)

- 3.2 Durable Event Sourcing (Nexus)

- 3.3 Agent Equivalence Registry (GHARRA)

# 4. Risk Mitigation Phase (After All Capabilities Pass)

Once all 6 capability gates pass, the 18 risk mitigations are implemented. Mitigations are ordered by phase and distributed across repos as documented in the per-repo mitigation plans.

| Phase | Mitigations | What Gets Built | Repo | Open Source Component |
| --- | --- | --- | --- | --- |
| Immediate | 1.1, 1.3, 2.3, 5.3 | TIA engine, enforcement proxy, multi-layer PHI detector, GDPR erasure pattern | All GHARRA | None (pure application code) |
| Pre-Launch | 1.2, 2.1, 5.1, 5.2 | DID-based sovereign identity, policy governance board, distributed ledger (Hyperledger Fabric), identifier standards (DIDs + LEIs) | All GHARRA | Hyperledger Fabric (Apache 2.0), did-resolver (Apache 2.0), GLEIF LEI API (CC0) |
| Post-Launch | 2.2, 3.1, 3.2, 3.3 | Break-glass governance with timestamp anchoring, IEC 62304 classification, durable event sourcing, agent equivalence registry | GHARRA: 2.2, 3.3; Nexus: 3.1, 3.2 | OpenTimestamps (LGPL 3.0) for break-glass anchoring |
| Scale | 4.1, 4.2, 4.3, 6.1, 6.2, 6.3 | Synthea populations, cloud deployment, benchmark tamper-proofing, framework validation, equity monitoring, ISCO-08 composable personas | Integration: 4.1, 4.2, 6.2; GHARRA: 4.3; Nexus: 6.1, 6.3 | Synthea (Apache 2.0), ISCO-08 (ILO public domain) |

Mitigation phase estimated: 20-30 additional working days after all capability gates pass. Immediate phase can overlap with Scale capabilities if Sprint 5 gates are green.

# 5. Full Timeline Summary

| Phase | Work | Days | Cumulative | Gate | Outcome |
| --- | --- | --- | --- | --- | --- |
| Build | Sprint 1: Scale Simulation | 3 | Day 1-3 | Smoke+Small pass | Test infrastructure working. Simulation reports generated. |
| Build | Sprint 2: Cross-Border Routing | 5 | Day 4-8 | Federation tests pass | Multi-sovereign federation working. Cross-border invocation proven. |
| Build | Sprint 3: Audit Trail | 5 | Day 9-13 | Ledger expansion tests pass | All routing+policy decisions auditable. Background verification. SSE streaming. |
| Build | Sprint 4: Policy Routing | 6 | Day 14-19 | Enforcement bridge tests pass | PHI auto-detected. Enforcement bridge live. Consent validated. Hot-reload works. |
| Build | Sprint 5: Persona Workflows | 5 | Day 20-24 | Persona routing tests pass | Framework drives avatar prompts. Persona influences routing. Country-aware. |
| Build | Sprint 6: Self-Healing Mesh | 8 | Day 25-32 | Failover tests pass | Handoff rules live in gateway. Stream resume. Automatic failover. Health probing. |
| Harden | Immediate Mitigations | 8 | Day 33-40 | TIA + PHI + Erasure tests | GDPR transfer checks, multi-layer PHI, erasure pattern operational. |
| Harden | Pre-Launch Mitigations | 8 | Day 41-48 | DID + Fabric + LEI tests | Hyperledger Fabric deployed. DIDs verified. LEI-based org identity. |
| Harden | Post-Launch Mitigations | 7 | Day 49-55 | Break-glass + IEC + Equiv tests | Break-glass anchored. IEC 62304 classified. Agent equivalence registry. |
| Harden | Scale Mitigations | 7 | Day 56-62 | Synthea + Equity + ISCO tests | Synthea populations. Equity monitoring. ISCO-08 composable personas. |

Total: ~62 working days (32 days capabilities + 30 days mitigations). Build phase ends at Day 32 with 6 proven capabilities. Harden phase ends at Day 62 with 18 risk mitigations and full regulatory readiness.

This plan transforms three separate repositories into a standards-compliant, blockchain-anchored, clinically-validated healthcare AI platform in ~12 working weeks using exclusively open source technology.